## Sheet1
Physical Quarterly Target (max length: 100 characters) | Physical Quarterly Achievement (max length: 100 characters) | Financial Quarterly Target (max length: 100 characters) | Financial Quarterly Target (max length: 100 characters)
Literature Survey of existing insulation products like rock-wool, glass-wool, etc. and their performance as thermal insulators & Acoustic - ongoing | Literature Survey of existing insulation products like rock-wool, glass-wool, etc. and their performance as thermal insulators & Acoustic - ongoing
Industry interaction initiated and attended round table conference on building insulation materials conducted by Centre of Pastoralism at Triveni Kala Sangam, Delhi | Industry interaction initiated and attended round table conference on building insulation materials conducted by Centre of Pastoralism at Triveni Kala Sangam, Delhi
Consumables purchased -partly. | Consumables purchased -partly.
Initial sampling of insulation material is being carried out. | Initial sampling of insulation material is being carried out.
Testing of developed panel w.r.to thermal insulation properties as per ASTM D 1518- ongoing | Testing of developed panel w.r.to thermal insulation properties as per ASTM D 1518- ongoing
Testing of developed porotype panel against moth proofing (Bioassay) | Testing of developed porotype panel against moth proofing (Bioassay)
Mothproofing treatment to loose scoured wool fiber using (Permethrin) for durable finish. | Mothproofing treatment to loose scoured wool fiber using (Permethrin) for durable finish.
Designing the wool-based insulation panels using natural bio-degradable honeycomb structured solution, which will be ready to fit in the building. | Designing the wool-based insulation panels using natural bio-degradable honeycomb structured solution, which will be ready to fit in the building.
Initial test results show that developed prototypes of thermal insulation panels need to be modified. | Initial test results show that developed prototypes of thermal insulation panels need to be modified.
Redesigning of panels are ongoing using 3-D corrugated light weight box which will be customized and ready for installation. | Redesigning of panels are ongoing using 3-D corrugated light weight box which will be customized and ready for installation.
Enhancing the thermal insulation of wool with graphene involves creating graphene oxide (GO) with particle sizes of 10.82 microns and over 54.29 microns. | Enhancing the thermal insulation of wool with graphene involves creating graphene oxide (GO) with particle sizes of 10.82 microns and over 54.29 microns.
Assessing the particle sizes, transforming GO into reduced graphene oxide (rGO), and applying it to a nonwoven material. | Assessing the particle sizes, transforming GO into reduced graphene oxide (rGO), and applying it to a nonwoven material.
Test: Particle size analysis | Test: Particle size analysis
Beckman Coulter LS13320 Laser Diffraction Particle Size Analyzer (Wet module) | Beckman Coulter LS13320 Laser Diffraction Particle Size Analyzer (Wet module)