## Sheet1
Physical Quarterly Target (max length: 100 characters) | Physical Quarterly Achievement (max length: 100 characters) | Financial Quarterly Target (max length: 100 characters) | Financial Quarterly Target (max length: 100 characters)
Literature Survey of existing insulation products like rock-wool, glass-wool, etc. and their performance as thermal insulators & Acoustic - ongoing | Literature Survey of existing insulation products like rock-wool, glass-wool, etc. and their performance as thermal insulators & Acoustic - ongoing
Industry interaction initiated and attended round table conference on building insulation materials conducted by Centre of Pastoralism at Triveni Kala Sangam, Delhi | Industry interaction initiated and attended round table conference on building insulation materials conducted by Centre of Pastoralism at Triveni Kala Sangam, Delhi
Consumables purchased -partly | Consumables purchased -partly
Initial sampling of insulation material is being carried out. | Initial sampling of insulation material is being carried out.
Testing of developed panel w.r.to thermal insulation properties as per ASTM D 1518 - ongoing | Testing of developed panel w.r.to thermal insulation properties as per ASTM D 1518 - ongoing
Testing of developed porotype panel against moth proofing (Bioassay) | Testing of developed porotype panel against moth proofing (Bioassay)
Mothproofing treatment to loose scoured wool fiber using (Permethrin) for durable finish. | Mothproofing treatment to loose scoured wool fiber using (Permethrin) for durable finish.
Designing the wool-based insulation panels using natural bio-degradable honeycomb structured solution, which will be ready to fit in the building. | Designing the wool-based insulation panels using natural bio-degradable honeycomb structured solution, which will be ready to fit in the building.
Initial test results show that developed prototypes of thermal insulation panels need to be modified. | Initial test results show that developed prototypes of thermal insulation panels need to be modified.
Redesigning of panels are ongoing using 3-D corrugated light weight box which will be customized and ready for installation. | Redesigning of panels are ongoing using 3-D corrugated light weight box which will be customized and ready for installation.