## Sheet2
Milestone | Target date
1st installment 60% of the grant at the time of sanction of the project | 0 months
Literature survey and organizing the experiments
procurement of raw material etc.
Development of eco friendly herbal based moth proofing finishing agents
Development of chemical based moth proofing finishing agents
2nd installment 30% | 12 months
Optimization and standardization of the recipe and process parameters
Benchmarking of developed product with commercial available products
3rd installment 10% | 24 months
Bulk scale trails and data evaluation
report writing and submussiion