## Sheet1
Time schedule of activities giving milestones
Activity | Quarter (03 month each)
Timeline: 24 months | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8
Coarse wool collection from Rajasthan, Maharashtra, Karnataka, and Telengana
Coarse wool characterization (diameter, medullation,length, bundle strength, moisture)
Keratin extraction using green solvent method
Keratin characterization and solubility studies
Keratin fluid preparation for electrospinning
Coarse wool keratin blend nanofibre preparation
Characterization of nanofibres
Textile structure preparation using keratin nanofibres
Determination of anti-bacterial performance of keratin nanofibres
Determination of wound healing rate on experimental animals
Project resort re saration, sro'ect worksho